## Test Summary Report
TEST REPORT
Project Name |  | HW05: GUI Testing |  |  | Creator |  | Tran Nhat Thanh
Group ID |  | 8 |  |  | Approver
Note | Two bugs are found in the previous report, so only 6 new added
| Test Coverage | 100% |  |  |  |  | Date: | 27/11/2025
| Successful Coverage | 73.29%
No. | Items | Tested | Passed | Failed | Blocked | Skipped | Not yet tested | Total | Test Coverage
1 | Guest: Search & Sort & Filter | 31 | 12 | 19 | 0 | 0 | 0 | 31 | 100%
2 | User: Checkout Flow | 41 | 31 | 10 | 0 | 0 | 0 | 41 | 100%
3 | Admin: Add/Edit Product | 35 | 30 | 5 | 0 | 0 | 0 | 35 | 100%
4 | GUI checklist | 54 | 45 | 9 | 0 | 0 | 0 | 54 | 100%
| Total | 161 | 118 | 43 | 0 | 0 | 0 | 161 | 100%

## Defect Severity Distribution
DEFECT SEVERITY DISTRIBUTION
No. | Items | Fatal | Serious | Medium | Cosmetic | Total
1 | Guest: Search & Sort & Filter | 0 | 3 | 1 | 0 | 4
2 | User: Checkout Flow | 1 | 5 | 1 | 3 | 10
3 | Admin: Add/Edit Product | 2 | 0 | 0 | 0 | 2
| Total | 3 | 8 | 2 | 3 | 16